## Jan to Mar
Department of Social Welfare and Development
Physical Report of Operation
(January to March 2014)
DEPARTMENT/AGENCY: Department of Social Welfare and Development
Program/activities/Projects MFO | Performance Indicators | Physical Targets |  | Actual | Percentage (%) of Accomplishment | Reason for Under/Over Performance (Variance)
|  | FY 2014 (Annual) | Jan to March | Jan to March
MFO 1: Social Protection Policy Services | QUANTITY No. of policies updated, issued and disseminated | [5 empty] | yes
| No. of policy notes issued | 4 | 1 |  |  | On-going finalization of the policy notes | yes
| No. of policy guidelines developed/ enhanced | 10 | 3 | 1 | 33.33% |  | yes
| No. of sectoral plans and implementation report prepared | 6 | 6 | 6 | 100%
| QUALITY Average % of Members of Congress, intermediaries and other stakeholders that rate policies as good or better | 90% |  |  |  | Survery is not scheduled in the first quarter
| TIMELINESS % of policies that are updated, issued and disseminated in the last three (3) years | 75% | 75%
MFO 2: Social Protection Services | QUANTITY No. of persons assisted
No. of persons provided with residential care
| Centers and Institutions | [5 empty] | yes
| No. of beneficiaries served at the facilities | 13340 | 3335 | 6247 | 187.3% |  | yes
Disaster Relief Operations
No. of beneficiaries provided with relief assistance
| Families | 1150231 |  | 251732 | 21.89%
| Individuals | 5331058 |  | 1139869 | 21.38%
Community-based
| No. of community-based beneficiaries provided with protective services | 157179 | 37703 | 19583 | 51.94% |  | yes
| Individuals | 58686 | 17019 | 11175 | 65.66%
| Clients served at Crisis Intervention Unit (CIU) | 98493 | 20684 | 8408 | 40.65% | Accomplishment is only based on the submission of 12 DSWD Field Offices | yes
| QUALITY % of assisted persons for the last three (3) years who were found ineligible (no more than averaged 5%) | 5% | 5% | 0%
| TIMELINESS 1 % of applications for non-residential assistance that are processed within 24 hours. | 90% | 90% | 98%
| TIMELINESS 2 % of applications for residential assistance that are processed within 24 hours. | 100% | 100% | 100%
Pantawid Pamilyang Pilipino Program (Conditional Cash Transfer)
| No. of household beneficiaries | 4329769 | 4329769 | 4004795 | 92.49%
Modified Conditional Cash Transfer e/
| No. of household beneficiaries | 131963 | 131963 | 2059 | 1.56% | Low accomplishment is due to the ongoing registration of IP eligible households
| No. of children beneficiaries - CCT extended Coverage until High School | 10196437 | 10196437 | 6399555
Supplementary Feeding Program
| No. of Day Care/School Children provided with supplementary feeding | 2568811 |  | 1674441 |  | Accomplishment is cumulative as of March 2014 of the third cycle implementation (SY 2013-2014), with target of 1,778,274
Recovery and Reintegration Program for Trafficked Persons
| No. of trafficked person assisted | 1000 | 250 | 665 | 266% | Included in the accomplishment are those rescued, offloaded by competent authorities such as Immigration Officers, port authorities and intercepted potential TIP victims in the transit areas like NCR, Region III and IX Inreased vulnerability of the Yolanda-affected victims and most of them who are trafficked are reported during the first quarter
Social Pension for Indigent Senior Citizens for ages 77 and above
| No. of indigent senior citizens with social pension for ages 77 and above | 479080 | 479080 |  |  | Field Offices has only started the pay-out last April 2014
Sustainable Livelihood Program
No. of families to be served through ME Development
| Pantawid Pamilya | 77912 | 31165 | 38934 | 124.9%
| No. of household facilitated for employment | 33402 | 13360.8 | 1805 | 13.51%
MFO 3: Capacity Building Services | PI SET 1
| QUANTITY No. of persons provided with training services | 5106 | 1772 | 3579 | 202% | Accomplishment are from DSWD Field Offices (FOs) |  | CBB - | FO - 3,579
| QUALITY % of trainees who rate training courses satisfactory or better | 90% | 90% | 94% |  | Accomplishment are from DSWD Field Offices (FOs) |  | CBB - | FO - 94%
| TIMELINESS % of training courses that completed as designed | 95% | 95% | 98% |  | Accomplishment are from DSWD Field Offices (FOs) |  | CBB - | FO - 98%
PI SET 2
| QUANTITY No. of LGUs and other intermediaries provided with technical assistance | 1133 | 458 | 868 | 189.5% | Accomplishment are from DSWD Field Offices (FOs) |  | PSB - | FO - 868
| QUALITY % of intermediaries who rate assistance as good or better | 90% | 90% | 96% |  | Accomplishment are from DSWD Field Offices (FOs) |  | PSB - | FO - 96%
| TIMELINESS % of technical services provided within X days of request | 100% | 100% | 99% |  | Accomplishment are from DSWD Field Offices (FOs) |  | PSB - | FO - 99%
PI SET 3
| QUANTITY No. of LGUs and other intermediaries provided with resource augmentation | 1106 | 253 | 451 | 178.3% | Accomplishment are from DSWD Field Offices (FOs) |  | DRRROO - | FO - 451
| QUALITY % of recipients who rate assistance as good or better | 90% | 90% | 100% |  | Accomplishment are from DSWD Field Offices (FOs) |  | DRRROO -
| TIMELINESS % of resource augmentation initiative requests acted upon within three (3) days. | 90% | 90% | 99% |  | Accomplishment are from DSWD Field Offices (FOs) |  | DRRROO - | FO - 99%
MFO 4: Regulatory Services | PI SET 1
| QUANTITY No. of social welfare and development agencies and service providers licensed or accredited | 482 | 98 | 910 |  | Includes accomplishment of FOs: SB (SWDA licensed) - 14 SB (SP accredited) - 42 FO (SWA licensed) - 26 FO (SP accredited) - 828 |  | SB (SWDA licensed) - 14 SB (SWDA accredited) - 8 SB (SP accredited) - 42 | FO (SWA licensed) - 26 FO (SP accredited) - 828
| QUALITY % of licensed and accredited SWDAs/ service providers with a recorded violation within the last two (2) years | 100% complaints acted upon | 100% complaints acted upon | 100% complaints acted upon |  |  |  | SB - 0 | FO - 100%
| TIMELINESS % of licenses issued in 15 days or less from receipt of compliant application | 100% | 100% | 80% |  |  |  | SB - 80%
PI SET 2
| QUANTITY Number of violations/ complaints received | 5 | 5 | 6 | 120% | Accomplishment are from DSWD Field Offices (FOs) |  | SB - 0 | FO - 6
| QUALITY Number of persons and entities with 2 or more recorded violations/ complaints in the last three (3) years as a % of total number of violators in the last three (3) years. | 100% complaints acted upon | 100% complaints acted upon | 100% complaints acted upon |  | Accomplishment are from DSWD Field Offices (FOs) |  | SB - 0 | FO - 100%
| TIMELINESS Percentage of detected violations/complaints that are resolved within seven (7) working days | 100% complaints acted upon | 100% complaints acted upon | 100% complaints acted upon |  | Accomplishment are from DSWD Field Offices (FOs) |  | SB - 0 | FO - 0
Locally-Funded Projects | Comprehensive Program for Street Children, Street Families and IPs, especially Bajaus
| No. of street children served | 3000 |  |  |  | Not targeted for the first quarter
| No. of Sama-Bajau children served | 606
| No. of street families served | 600
| No. of Bajau families served | 700 | [7 empty] | 0
National Household Targeting System for Poverty Reduction
| Number of households identified as poor through the Proxy Means Test (PMT) | 5.7 million poor households |  |  |  | Not targeted for the first quarter
Implementation of various programs/projects for LGUs (Priority Programs)
Bottom-Up Budgeting
No. of LGUs benefitted from the following programs:
| Protective Services |  |  |  |  | All targeted ares are in social preparation stage
| SEA-K (No. of Municipalities served) |  |  |  |  | Centrally-managed funds were just downloaded
| NCDDP |  |  |  |  | Documents review and on-site validation of proposed projects are still ongoing
Implementation and Monitoring of PAMANA Program
No. of Provinces
No. of Barangays
| NCDDP | 1,380 Brgys; 18 Provinces |  |  |  | All targeted areas are in social preparation stage
| SLP | 470 Brgys; 9 Provinces |  |  |  | Field Offices are currently in the process of procuring the equipment/common service facilities for the projects
| PAMANA Pillar 2 | 268 Brgys; 5 Provinces |  |  |  | All targeted areas are in social preparation stage
0
Prepared By: |  | Approved By:
___________________________ |  | _____________________________________
FLORITA R. VILLAR |  | CORAZON JULIANO-SOLIMAN
Undersecretay for Policy and Plans Group |  | Secretary
Note on D36: acer: used the original submitted targets of Pantawid. Not the one refelcted in the GAA for CY 2014

## JantoSep (hidden)
Department of Social Welfare and Development
Physical Report of Operation
(January to September 2013)
DEPARTMENT/AGENCY: Department of Social Welfare and Development
Key Program/activities/Projects (P/A/Ps) | Performance Indicators | Physical Targets |  | Actual | Percentage (%) of Accomplishment | Reason for Under/Over Performance (Variance)
|  | FY 2013 (Annual) | Jan to Sep | Jan to Sep
MFO 1
Services Relating to the Formulation of Policies, Plans and Programs | [7 empty] | Formula?
Policies and Plans Development | No. of policy/position papers prepared including policies on regional cooperation international treaties and conventions | 44 | #REF! | #REF! | #REF! |  |  | yes
| No. of policy notes issued | 4 | #REF! | #REF! | #REF! |  |  | yes
| No. of policy guidelines developed/enhanced | 9 | #REF! | #REF! | #REF! |  |  | yes
| No. of LGUs monitored complying to national and local laws/polices | 573 | #REF! | #REF! | #REF! |  |  | yes
| No. of LGUs with SWD sectoral plans (cities,municipalities) | 678 | #REF! | #REF! | #REF! |  |  | yes
| No. of sectoral plans and implementation report prepared | 6 | 6 | 6 | 100
| No. of research developed /implemented / completed | 8 | #REF! | #REF! | #REF! |  |  | yes
| E-Services Upgraded | For enhancement | For enhancement | For enhancement
| SWD Geographic Information System (GIS) Developed | Continuous Updating | Continuous Updating | Continuous Updating
Social Welfare Development Reform Project (SWDRP) | National Convergence Framework on SP | Adoption of National Convergence Framework | #REF! | #REF! |  | Not targeted for the first quarter |  | yes
| Five (5) year Social Protection Plan | Implementation of 5 year SP Plan | #REF! | #REF! |  | Not targeted for the first quarter |  | yes
| Social Protection Handbook (draft) | 1 | #REF! | #REF! |  | Not targeted for the first quarter |  | yes
| Policies/Research Studies on Social Protection | 2 | 2 |  |  | deleted by PRD?
| Manual on Risk and Vulnerability (SP VAM) | 1 | #REF! | #REF! |  | Not targeted for the first quarter |  | yes
| Monitoring and Evaluation Unit (establishment) | Maintained 1 Monitoring and Evaluation Unit | Maintained 1 Monitoring and Evaluation Unit | Maintained 1 Monitoring and Evaluation Unit
| Impact Evaluation Conducted | 2 | 1
| Operational Manual on M & E | 1 | 1 | Ongoing finalization of the M&E OM
| Index and Measure on Prevalance rate of Risk and Vulnerabilies Assessment | 1
| Regional Sectoral participation Index Developed | 1
Program Development | No. of social technology developed/programs and services enhanced | 2 | #REF! | #REF! |  | Not targeted for the first quarter | ask for reasons | yes
| No. of social technology guidelines developed | 3 |  | 1 |  | Carry-over from last year's activity
| No. of manual developed and/or finalized | 2 | #REF! | #REF! |  | Not targeted for the first quarter |  | yes
| No. of concept paper/program design and documentation completed | 4 |  | 3 |  | Carry-over from last year's activity
| No. of foreign post established to deliver SWD services to Filipino nationals | 8 | 8
National Household Targeting System for Poverty Reduction (NHTS-PR)
| Targetting System for SWD programs | Maintained 1 Targeting System | Maintained 1 Targeting System | Maintained 1 Targeting System
| No. of household assessed and included in the database | Maintained 10,909,456 HHs in the database | Maintained 10,909,456 HHs in the database | Maintained 10,909,456 HHs in the database
| Number of households identified as poor through the Proxy Means Test (PMT) | Maintained 5.2 Million households in the database | Maintained 5.2 Million households in the database | Maintained 5.2 Million households in the database
MFO 2
Standards Setting, Licensing and Accreditation Services
Standards Setting and Accreditation Services | No. of auxiliary SWDAs registered | 211 | #REF! | #REF! | #REF! |  |  | yes
| No. of SWAs registered and licensed (NGOs licensed) | 191 | #REF! | #REF! | #REF! |  |  | yes
| No. of SWAs accredited (NGOs accredited) | 96 | #REF! | #REF! | #REF! |  |  | yes
| No. of SWD Service providers accredited ( marriage counsellors, social workers, handling court cases, day care workers) | 2987 | #REF! | #REF! | #REF! |  |  | yes
| No. of service facilities accredited (Day Care Center;Senior Citizens Centers) | 2886 | #REF! | #REF! | #REF! |  |  | yes
| No. of NGOs endorsed to the Department of Finance | As Need Arises (ANA) | ANA | 9
| No. of Authorities issued to conduct National Fund Raising Campaigns | ANA | ANA | 4
| No. of ABSNET clusters organized and strengthened | 61 | 61 | 61 | 100
Reform Agenda | Online database for SWADA/service providers completed | Maintained & Sustained Online Database | Maintained & Sustained Database | Ongoing updating of the database
| Consultation meetings with ABSNET by Field Offices | 61 |  |  |  | Not targeted for the first quarter
| Consultation meeting with National ABSNET Federation | 1 | #REF! | #REF! |  | Not targeted for the first quarter |  | yes
| National Consultation Dialogues | 1 | #REF! | #REF! |  | Not targeted for the first quarter |  | yes
| Development of Manual on Monitoring and Evaluation of SWADAs | 1 | #REF! | #REF! |  | Not targeted for the first quarter |  | yes
| Evaluation of the Accreditation System for Social Welfare and Development Programs and Services | 5 | #REF! | #REF! |  | Not targeted for the first quarter |  | yes
MFO 3
Provision of Support Services and Technical Assistance to Intermediaries
Support Services and Technical Assistance to Intermediaries | No. of existing SWD training modules developed | 13 | #REF! | #REF! |  | Not targeted for the first quarter |  | yes
| No. of existing SWD training modules enhanced | 40 | #REF! | #REF! | #REF! |  |  | yes
| No. of training modules utilized by intermediaries | 73 | #REF! | #REF! | #REF! |  |  | yes
| No. of trainings conducted | 278 | #REF! | #REF! | #REF! |  |  | yes
| No. of SWD implementers trained | 3040 | #REF! | #REF! | #REF! |  |  | yes
| No. of participants who completed training | 9683 | #REF! | #REF! | #REF! |  |  | yes
Social Welfare Development Reform Project (SWDRP) | Knowledge Management and Learning Division Established | Maintained 1 Knowledge Management and Learning Development | Maintained 1 Knowledge Management and Learning Development | Maintained 1 Knowledge Management and Learning Development
| Knowledge Exchange Center Established | Maintained 1 Knowledge Exchange Center | Maintained 1 Knowledge Exchange Center | Maintained 1 Knowledge Exchange Center
Disaster Relief Operations | No. of beneficiaries provided with relief assistance
| Families | ANA | ANA | #REF! |  |  |  | yes
| Individuals | ANA | ANA | #REF! |  |  |  | yes
No. of disaster affected LGUs provided augmentation support
| Provinces | ANA | ANA | #REF! |  |  |  | yes
| Cities | ANA | ANA | #REF! |  |  |  | yes
| Municipalities | ANA | ANA | #REF! |  |  |  | yes
SEA Kaunlaran Program
No. of families provided with capital seed fund
| Pantawid Pamilya | 486586 | 174086 | 19064 | 10.9509 | Reflected figures are only those provided with capital seed fund by DSWD. However, through partneship with Micro-Finance Institutions, a total of 24,554 Pantawid Pamilya beneficiaries were provided with capital assistance. Further, skills-enhancement training on farming and production were given to 13,447 Pantawid Pamilya beneficiaries as a form of non-financial assistance and facilitated employment of 77 pantawid beneficiaries.
| Non-Pantawid |  |  | 3674
Supplementary Feeding Program
| No. of Day Care Children provided with supplementary feeding | 1778274 | 1755034 | 1664227 | 94.8259 | Accomplishments are as of the March 2013 of the Second Cycle of the program SY 2012-2013
Cash/Food for Work/Training Program for Internally Displaced Person (IDPs)
| No. of IDPs affected by typhoon and other calamities manmade/natural provided with cash/training/work | 253881.0153 | 253881.0153
Core Shelter
| No. of shelter units funded | ANA | ANA | 400
| No. of shelter units completed/ongoing | ANA | ANA | 105
| No. of families benefited | ANA | ANA | 400
Payapa at Masaganang Pamayanan (PAMANA)
| No. of barangays for community-driven development projects in ARMM | 2159 | #REF! | #REF! | #REF! |  |  | yes
Recovery and Reintegration Program for Victims-Survivors of Trafficking
| Number of trafficked person assisted/services provided | 925 | #REF! | #REF! | #REF! |  |  | yes
| Number of LGU Social Workers trained to provide psychosocial recovery, and social and economic reintegration services to victims-survivors of trafficking | 500 | #REF! | #REF! | #REF! |  |  | yes
| Number of regions with functional Recovery and Reintegration Network | 17 | #REF! | #REF! | #REF! |  |  | yes
| Centers upgraded to accommodate victims-survivors of trafficking | 6 | 6 |  |  | No centers upgraded yet for this quarter
MFO 4
Services for Center-Based and Community-Based Clients
Centers and Institutions
| No. of beneficiaries served at the facilities | 13182 | #REF! | #REF! | #REF! |  |  | yes
| No. of client days of service at the facilities | 1642170 | 1642170 | 396534 | 24.147
| No. of clients released/discharged from the facilities | 7163 | #REF! | #REF! | #REF! |  |  | yes
| No. of client rehabilitated at the facilities | 6201 | #REF! | #REF! | #REF! |  |  | yes
Community-based Services | No. of community-based beneficiaries provided with protective services Individuals | 58892 | #REF! | #REF! | #REF! |  |  | yes
| No. of clients served at Crisis Intervention Unit (CIU) | 93803 | #REF! | #REF! | #REF! | Provision of services to disaster victims of tropical storm "Quinta" and other clients (using the Priority Development Assistance Fund (PDAF) in Region VI thru DSWD CIU contributes largely to the over performance of this indicator. |  | yes
Social Pension for Indigent Senior Citizens for ages 77 and above
| No. of indigent senior citizens provided with social pension for ages 77 and above | 240868 | 240868 | 36309 | 15.0742 | Reported accomplishment is only as of 31 March 2013. Completion of pay-out to all beneficiaries is targeted to be done within the month of April 2013 or the next month following the reference quarter.
Program for Street Children, Street families and IPs, especially Bajaus
| No. of street children and their families served at day/night centers/activity centers a. Street Children b. Street Families | Continuous provision of support services like skills training, livelihood, relocation to street children, street families, Ips and Bajaus | ANA
| No. of street children provided with educational assistance | 2000 | #REF! | #REF! |  | Not targeted for the first quarter |  | yes
| No. Bajau families/street families provided with Balik Probinsya Assistance | 20 | #REF! | #REF! |  | Not targeted for the first quarter |  | yes
| No. of parents provided with livelihood assistance | 180 | #REF! | #REF! |  | Not targeted for the first quarter |  | yes
| No. of street families/Bajau families provided with permanent shelter | 80 | #REF! | #REF! |  | Not targeted for the first quarter |  | yes
| No. of bajau families provided with livelihood and capacity building activities | 500 | #REF! | #REF! |  | Not targeted for the first quarter |  | yes
Pantawid Pamilyang Pilipino Program (Conditional Cash Transfer)
No. of household beneficiaries
| No. of targeted: | 3809769 | 3809769 | 3967517 | 104.1406
| Regions | 17 | 17 | 17
| Provinces | 79 | 79 | 79
| Cities/Municipalities | 143cities, 1,484mun. | 143cities, 1,484mun. | 143cities, 1,484mun.
Foreign-Assisted Project KCI KC Additional Financing (AF) KC Millennium Challenge Corporation (MCC) | No. of areas covered by KALAHI-CIDSS
| Regions | 12 |  | 12
| Provinces | 36 |  | 36
| Municipalities | 158 |  | 158
| Barangays | 3789 |  | 3789
| No. of household beneficiaries from completed community sub-projects | 396900 | 50064 | 41082 | 82.059
| No. of community development projects completed | 1764 |  | 207
No. of LGUs fully implemented/intitutionalized the KC process (LGUs that adopting features of the KC approach)
| Municipalities | 148 |  | onging implementation
| Barangays | 3529 |  | onging implementation
0
Prepared By: |  | Approved By:
___________________________ |  | _____________________________________
FLORITA R. VILLAR |  | CORAZON JULIANO-SOLIMAN
Undersecretay for Policy and Plans Group |  | Secretary
Highlighted in green are those indicators that were included in the 2013 APM but not reflected in the CY 2013 BEDs

## JantoDec (hidden)
Department of Social Welfare and Development
Physical Report of Operation
(January to December 2013)
DEPARTMENT/AGENCY: Department of Social Welfare and Development
Key Program/activities/Projects (P/A/Ps) | Performance Indicators | Physical Targets |  | Actual | Percentage (%) of Accomplishment | Reason for Under/Over Performance (Variance)
|  | FY 2013 (Annual) | Jan to Dec | Jan to Dec
MFO 1
Services Relating to the Formulation of Policies, Plans and Programs | [7 empty] | Formula?
Policies and Plans Development | No. of policy/position papers prepared including policies on regional cooperation international treaties and conventions | 44 | #REF! | #REF! | #REF! |  |  | yes
| No. of policy notes issued | 4 | #REF! | #REF! | #REF! |  |  | yes
| No. of policy guidelines developed/enhanced | 9 | #REF! | #REF! | #REF! |  |  | yes
| No. of LGUs monitored complying to national and local laws/polices | 573 | #REF! | #REF! | #REF! |  |  | yes
| No. of LGUs with SWD sectoral plans (cities,municipalities) | 678 | #REF! | #REF! | #REF! |  |  | yes
| No. of sectoral plans and implementation report prepared | 6 | 6 | 6 | 100
| No. of research developed /implemented / completed | 8 | #REF! | #REF! | #REF! |  |  | yes
| E-Services Upgraded | For enhancement | For enhancement | For enhancement
| SWD Geographic Information System (GIS) Developed | Continuous Updating | Continuous Updating | Continuous Updating
Social Welfare Development Reform Project (SWDRP) | National Convergence Framework on SP | Adoption of National Convergence Framework | #REF! | #REF! |  | Not targeted for the first quarter |  | yes
| Five (5) year Social Protection Plan | Implementation of 5 year SP Plan | #REF! | #REF! |  | Not targeted for the first quarter |  | yes
| Social Protection Handbook (draft) | 1 | #REF! | #REF! |  | Not targeted for the first quarter |  | yes
| Policies/Research Studies on Social Protection | 2 | 2 |  |  | deleted by PRD?
| Manual on Risk and Vulnerability (SP VAM) | 1 | #REF! | #REF! |  | Not targeted for the first quarter |  | yes
| Monitoring and Evaluation Unit (establishment) | Maintained 1 Monitoring and Evaluation Unit | Maintained 1 Monitoring and Evaluation Unit | Maintained 1 Monitoring and Evaluation Unit
| Impact Evaluation Conducted | 2 | 1
| Operational Manual on M & E | 1 | 1 | Ongoing finalization of the M&E OM
| Index and Measure on Prevalance rate of Risk and Vulnerabilies Assessment | 1
| Regional Sectoral participation Index Developed | 1
Program Development | No. of social technology developed/programs and services enhanced | 2 | #REF! | #REF! |  | Not targeted for the first quarter | ask for reasons | yes
| No. of social technology guidelines developed | 3 |  | 1 |  | Carry-over from last year's activity
| No. of manual developed and/or finalized | 2 | #REF! | #REF! |  | Not targeted for the first quarter |  | yes
| No. of concept paper/program design and documentation completed | 4 |  | 3 |  | Carry-over from last year's activity
| No. of foreign post established to deliver SWD services to Filipino nationals | 8 | 8
National Household Targeting System for Poverty Reduction (NHTS-PR)
| Targetting System for SWD programs | Maintained 1 Targeting System | Maintained 1 Targeting System | Maintained 1 Targeting System
| No. of household assessed and included in the database | Maintained 10,909,456 HHs in the database | Maintained 10,909,456 HHs in the database | Maintained 10,909,456 HHs in the database
| Number of households identified as poor through the Proxy Means Test (PMT) | Maintained 5.2 Million households in the database | Maintained 5.2 Million households in the database | Maintained 5.2 Million households in the database
MFO 2
Standards Setting, Licensing and Accreditation Services
Standards Setting and Accreditation Services | No. of auxiliary SWDAs registered | 211 | #REF! | #REF! | #REF! |  |  | yes
| No. of SWAs registered and licensed (NGOs licensed) | 191 | #REF! | #REF! | #REF! |  |  | yes
| No. of SWAs accredited (NGOs accredited) | 96 | #REF! | #REF! | #REF! |  |  | yes
| No. of SWD Service providers accredited ( marriage counsellors, social workers, handling court cases, day care workers) | 2987 | #REF! | #REF! | #REF! |  |  | yes
| No. of service facilities accredited (Day Care Center;Senior Citizens Centers) | 2886 | #REF! | #REF! | #REF! |  |  | yes
| No. of NGOs endorsed to the Department of Finance | As Need Arises (ANA) | ANA | 9
| No. of Authorities issued to conduct National Fund Raising Campaigns | ANA | ANA | 4
| No. of ABSNET clusters organized and strengthened | 61 | 61 | 61 | 100
Reform Agenda | Online database for SWADA/service providers completed | Maintained & Sustained Online Database | Maintained & Sustained Database | Ongoing updating of the database
| Consultation meetings with ABSNET by Field Offices | 61 |  |  |  | Not targeted for the first quarter
| Consultation meeting with National ABSNET Federation | 1 | #REF! | #REF! |  | Not targeted for the first quarter |  | yes
| National Consultation Dialogues | 1 | #REF! | #REF! |  | Not targeted for the first quarter |  | yes
| Development of Manual on Monitoring and Evaluation of SWADAs | 1 | #REF! | #REF! |  | Not targeted for the first quarter |  | yes
| Evaluation of the Accreditation System for Social Welfare and Development Programs and Services | 5 | #REF! | #REF! |  | Not targeted for the first quarter |  | yes
MFO 3
Provision of Support Services and Technical Assistance to Intermediaries
Support Services and Technical Assistance to Intermediaries | No. of existing SWD training modules developed | 13 | #REF! | #REF! |  | Not targeted for the first quarter |  | yes
| No. of existing SWD training modules enhanced | 40 | #REF! | #REF! | #REF! |  |  | yes
| No. of training modules utilized by intermediaries | 73 | #REF! | #REF! | #REF! |  |  | yes
| No. of trainings conducted | 278 | #REF! | #REF! | #REF! |  |  | yes
| No. of SWD implementers trained | 3040 | #REF! | #REF! | #REF! |  |  | yes
| No. of participants who completed training | 9683 | #REF! | #REF! | #REF! |  |  | yes
Social Welfare Development Reform Project (SWDRP) | Knowledge Management and Learning Division Established | Maintained 1 Knowledge Management and Learning Development | Maintained 1 Knowledge Management and Learning Development | Maintained 1 Knowledge Management and Learning Development
| Knowledge Exchange Center Established | Maintained 1 Knowledge Exchange Center | Maintained 1 Knowledge Exchange Center | Maintained 1 Knowledge Exchange Center
Disaster Relief Operations | No. of beneficiaries provided with relief assistance
| Families | ANA | ANA | #REF! |  |  |  | yes
| Individuals | ANA | ANA | #REF! |  |  |  | yes
No. of disaster affected LGUs provided augmentation support
| Provinces | ANA | ANA | #REF! |  |  |  | yes
| Cities | ANA | ANA | #REF! |  |  |  | yes
| Municipalities | ANA | ANA | #REF! |  |  |  | yes
SEA Kaunlaran Program
No. of families provided with capital seed fund
| Pantawid Pamilya | 486586 | 174086 | 19064 | 10.9509 | Reflected figures are only those provided with capital seed fund by DSWD. However, through partneship with Micro-Finance Institutions, a total of 24,554 Pantawid Pamilya beneficiaries were provided with capital assistance. Further, skills-enhancement training on farming and production were given to 13,447 Pantawid Pamilya beneficiaries as a form of non-financial assistance and facilitated employment of 77 pantawid beneficiaries.
| Non-Pantawid |  |  | 3674
Supplementary Feeding Program
| No. of Day Care Children provided with supplementary feeding | 1778274 | 1755034 | 1664227 | 94.8259 | Accomplishments are as of the March 2013 of the Second Cycle of the program SY 2012-2013
Cash/Food for Work/Training Program for Internally Displaced Person (IDPs)
| No. of IDPs affected by typhoon and other calamities manmade/natural provided with cash/training/work | 253881.0153 | 253881.0153
Core Shelter
| No. of shelter units funded | ANA | ANA | 400
| No. of shelter units completed/ongoing | ANA | ANA | 105
| No. of families benefited | ANA | ANA | 400
Payapa at Masaganang Pamayanan (PAMANA)
| No. of barangays for community-driven development projects in ARMM | 2159 | #REF! | #REF! | #REF! |  |  | yes
Recovery and Reintegration Program for Victims-Survivors of Trafficking
| Number of trafficked person assisted/services provided | 925 | #REF! | #REF! | #REF! |  |  | yes
| Number of LGU Social Workers trained to provide psychosocial recovery, and social and economic reintegration services to victims-survivors of trafficking | 500 | #REF! | #REF! | #REF! |  |  | yes
| Number of regions with functional Recovery and Reintegration Network | 17 | #REF! | #REF! | #REF! |  |  | yes
| Centers upgraded to accommodate victims-survivors of trafficking | 6 | 6 |  |  | No centers upgraded yet for this quarter
MFO 4
Services for Center-Based and Community-Based Clients
Centers and Institutions
| No. of beneficiaries served at the facilities | 13182 | #REF! | #REF! | #REF! |  |  | yes
| No. of client days of service at the facilities | 1642170 | 1642170 | 396534 | 24.147
| No. of clients released/discharged from the facilities | 7163 | #REF! | #REF! | #REF! |  |  | yes
| No. of client rehabilitated at the facilities | 6201 | #REF! | #REF! | #REF! |  |  | yes
Community-based Services | No. of community-based beneficiaries provided with protective services Individuals | 58892 | #REF! | #REF! | #REF! |  |  | yes
| No. of clients served at Crisis Intervention Unit (CIU) | 93803 | #REF! | #REF! | #REF! | Provision of services to disaster victims of tropical storm "Quinta" and other clients (using the Priority Development Assistance Fund (PDAF) in Region VI thru DSWD CIU contributes largely to the over performance of this indicator. |  | yes
Social Pension for Indigent Senior Citizens for ages 77 and above
| No. of indigent senior citizens provided with social pension for ages 77 and above | 240868 | 240868 | 36309 | 15.0742 | Reported accomplishment is only as of 31 March 2013. Completion of pay-out to all beneficiaries is targeted to be done within the month of April 2013 or the next month following the reference quarter.
Program for Street Children, Street families and IPs, especially Bajaus
| No. of street children and their families served at day/night centers/activity centers a. Street Children b. Street Families | Continuous provision of support services like skills training, livelihood, relocation to street children, street families, Ips and Bajaus | ANA
| No. of street children provided with educational assistance | 2000 | #REF! | #REF! |  | Not targeted for the first quarter |  | yes
| No. Bajau families/street families provided with Balik Probinsya Assistance | 20 | #REF! | #REF! |  | Not targeted for the first quarter |  | yes
| No. of parents provided with livelihood assistance | 180 | #REF! | #REF! |  | Not targeted for the first quarter |  | yes
| No. of street families/Bajau families provided with permanent shelter | 80 | #REF! | #REF! |  | Not targeted for the first quarter |  | yes
| No. of bajau families provided with livelihood and capacity building activities | 500 | #REF! | #REF! |  | Not targeted for the first quarter |  | yes
Pantawid Pamilyang Pilipino Program (Conditional Cash Transfer)
No. of household beneficiaries
| No. of targeted: | 3809769 | 3809769 | 3967517 | 104.1406
| Regions | 17 | 17 | 17
| Provinces | 79 | 79 | 79
| Cities/Municipalities | 143cities, 1,484mun. | 143cities, 1,484mun. | 143cities, 1,484mun.
Foreign-Assisted Project KCI KC Additional Financing (AF) KC Millennium Challenge Corporation (MCC) | No. of areas covered by KALAHI-CIDSS
| Regions | 12 |  | 12
| Provinces | 36 |  | 36
| Municipalities | 158 |  | 158
| Barangays | 3789 |  | 3789
| No. of household beneficiaries from completed community sub-projects | 396900 | 50064 | 41082 | 82.059
| No. of community development projects completed | 1764 |  | 207
No. of LGUs fully implemented/intitutionalized the KC process (LGUs that adopting features of the KC approach)
| Municipalities | 148 |  | onging implementation
| Barangays | 3529 |  | onging implementation
0
Prepared By: |  | Approved By:
___________________________ |  | _____________________________________
FLORITA R. VILLAR |  | CORAZON JULIANO-SOLIMAN
Undersecretay for Policy and Plans Group |  | Secretary
Highlighted in green are those indicators that were included in the 2013 APM but not reflected in the CY 2013 BEDs

## JultoSep (hidden)
Department of Social Welfare and Development
Physical Report of Operation
(July to September 2013)
DEPARTMENT/AGENCY: Department of Social Welfare and Development
Key Program/activities/Projects (P/A/Ps) | Performance Indicators | Physical Targets |  | Actual | Percentage (%) of Accomplishment | Reason for Under/Over Performance (Variance)
|  | FY 2013 (Annual) | Jul to Sep | Jul to Sep
MFO 1
Services Relating to the Formulation of Policies, Plans and Programs | [7 empty] | Formula?
Policies and Plans Development | No. of policy/position papers prepared including policies on regional cooperation international treaties and conventions | 44 | 12 |  | 0 |  |  | yes
| No. of policy notes issued | 4 | 1 |  | 0 |  |  | yes
| No. of policy guidelines developed/enhanced | 9 | 3 |  | 0 |  |  | yes
| No. of LGUs monitored complying to national and local laws/polices | 573 | 143 |  | 0 |  |  | yes
| No. of LGUs with SWD sectoral plans (cities,municipalities) | 678 | 170 |  | 0 |  |  | yes
| No. of sectoral plans and implementation report prepared | 6 | 6 |  | 0
| No. of research developed /implemented / completed | 8 | 2 |  | 0 |  |  | yes
| E-Services Upgraded | For enhancement | For enhancement
| SWD Geographic Information System (GIS) Developed | Continuous Updating | Continuous Updating
Social Welfare Development Reform Project (SWDRP) | National Convergence Framework on SP | Adoption of National Convergence Framework |  |  |  | not targeted for the thrid quarter |  | yes
| Five (5) year Social Protection Plan | Implementation of 5 year SP Plan | [5 empty] | yes
| Social Protection Handbook (draft) | 1 | 1 |  |  |  |  | yes
| Policies/Research Studies on Social Protection | 2 | 2 |  |  | deleted by PRD?
| Manual on Risk and Vulnerability (SP VAM) | 1 |  |  |  | Not targeted for the third quarter |  | yes
| Monitoring and Evaluation Unit (establishment) | Maintained 1 Monitoring and Evaluation Unit | Maintained 1 Monitoring and Evaluation Unit
| Impact Evaluation Conducted | 2 | 1
| Operational Manual on M & E | 1 | 1 |  |  |  | Ask nalang Aljo
| Index and Measure on Prevalance rate of Risk and Vulnerabilies Assessment | 1
| Regional Sectoral participation Index Developed | 1
Program Development | No. of social technology developed/programs and services enhanced | 2 |  |  |  | Not targeted for the first quarter, all of the 5 targets are to be accomplished on the last quarter of CY 2013. | checked the submission of STB regarding the revision of STB's quarterly targets for CY 2013 | yes
| No. of social technology guidelines developed | 3 |  |  |  | Sttill not targeted for the second quarter however, there's a carry-over from last year's activity which was already reported on the fist quarter physical report of operations
| No. of manual developed and/or finalized | 2 |  |  |  | Not targeted for the second quarter. | STB has revised its targets for this year from 2 to 5 manuals/developed or finalized | yes
| No. of concept paper/program design and documentation completed | 4 |  |  |  | Sttill not targeted for the second quarter however, there's a carry-over from last year's activity which was already reported on the fist quarter physical report of operations | STB has submitted revised targets for CY 2013. Check the submission of STB.
| No. of foreign post established to deliver SWD services to Filipino nationals | 8 | 8
National Household Targeting System for Poverty Reduction (NHTS-PR)
| Targetting System for SWD programs | Maintained 1 Targeting System | Maintained 1 Targeting System
| No. of household assessed and included in the database | Maintained 10,909,456 HHs in the database | Maintained 10,909,456 HHs in the database
| Number of households identified as poor through the Proxy Means Test (PMT) | Maintained 5.2 Million households in the database | Maintained 5.2 Million households in the database
MFO 2
Standards Setting, Licensing and Accreditation Services
Standards Setting and Accreditation Services | No. of auxiliary SWDAs registered | 211 | 53 |  | 0 |  | check the submission of SB (or kay ate tess since nasa kanya ang consolidatio ng MFO 2 reports | yes
| No. of SWAs registered and licensed (NGOs licensed) | 191 | 48 |  | 0 |  |  | yes
| No. of SWAs accredited (NGOs accredited) | 96 | 25 |  | 0 |  |  | yes
| No. of SWD Service providers accredited ( marriage counsellors, social workers, handling court cases, day care workers) | 2987 | 760 |  | 0 |  |  | yes
| No. of service facilities accredited (Day Care Center;Senior Citizens Centers) | 2886 | 719 |  | 0 |  |  | yes
| No. of NGOs endorsed to the Department of Finance | As Need Arises (ANA) | ANA
| No. of Authorities issued to conduct National Fund Raising Campaigns | ANA | ANA
| No. of ABSNET clusters organized and strengthened | 61 | 61 |  | 0 |  | whole year target which was already accomplished last first quarter
Reform Agenda | Online database for SWADA/service providers completed | Maintained & Sustained Online Database | Maintained & Sustained Database
| Consultation meetings with ABSNET by Field Offices | 61 |  |  |  | annual target
| Consultation meeting with National ABSNET Federation | 1 |  |  |  | annual target |  | yes
| National Consultation Dialogues | 1 |  |  |  | annual target |  | yes
| Development of Manual on Monitoring and Evaluation of SWADAs | 1 |  |  |  | annual target | requested for deletion last 7 June 2012 | yes
| Evaluation of the Accreditation System for Social Welfare and Development Programs and Services | 5 |  |  |  | annual target | requested to change the indicator to Development of a Quality Management System (QMS) Certifiable to ISO 9001:2008 for the DSWD Standards Bureau | yes
MFO 3
Provision of Support Services and Technical Assistance to Intermediaries
Support Services and Technical Assistance to Intermediaries | No. of existing SWD training modules developed | 13 |  |  |  | Not targeted for the third quarter |  | yes
| No. of existing SWD training modules enhanced | 40 | 10 |  | 0 |  |  | yes
| No. of training modules utilized by intermediaries | 73 | 18 |  | 0 |  |  | yes
| No. of trainings conducted | 278 | 70 |  | 0 |  |  | yes
| No. of SWD implementers trained | 3040 | 760 |  | 0 |  |  | yes
| No. of participants who completed training | 9683 | 2421 |  | 0 |  |  | yes
Social Welfare Development Reform Project (SWDRP) | Knowledge Management and Learning Division Established | Maintained 1 Knowledge Management and Learning Development | Maintained 1 Knowledge Management and Learning Development
| Knowledge Exchange Center Established | Maintained 1 Knowledge Exchange Center | Maintained 1 Knowledge Exchange Center
Disaster Relief Operations | No. of beneficiaries provided with relief assistance
| Families | ANA | ANA |  |  |  |  | yes
| Individuals | ANA | ANA |  |  |  |  | yes
No. of disaster affected LGUs provided augmentation support
| Provinces | ANA | ANA |  |  |  |  | yes
| Cities | ANA | ANA |  |  |  |  | yes
| Municipalities | ANA | ANA |  |  |  |  | yes
SEA Kaunlaran Program
No. of families provided with capital seed fund
| Pantawid Pamilya | 486586 | 174086 |  | 0 | Reflected figures are only those provided with capital seed fund by DSWD. However, through partneship with Micro-Finance Institutions, a total of 24,554 Pantawid Pamilya beneficiaries were provided with capital assistance. Further, skills-enhancement training on farming and production were given to 13,447 Pantawid Pamilya beneficiaries as a form of non-financial assistance and facilitated employment of 77 pantawid beneficiaries. | apply nalang siguro dito ung changes na gusto ni Dir. Geo-Ann
Non-Pantawid
Supplementary Feeding Program
| No. of Day Care Children provided with supplementary feeding | 1778274 | 1755034 |  | 0 | Accomplishments are as of the March 2013 of the Second Cycle of the program SY 2012-2013 | not clear ang targets for the second quarter based on the BED. Should it be the same based on their approved WFP?
Cash/Food for Work/Training Program for Internally Displaced Person (IDPs)
| No. of IDPs affected by typhoon and other calamities manmade/natural provided with cash/training/work | 253881.0153 | 253881.0153
Core Shelter
| No. of shelter units funded | ANA | ANA
| No. of shelter units completed/ongoing | ANA | ANA
| No. of families benefited | ANA | ANA
Payapa at Masaganang Pamayanan (PAMANA)
| No. of barangays for community-driven development projects in ARMM | 2159 | 540 |  | 0 |  |  | yes
Recovery and Reintegration Program for Victims-Survivors of Trafficking
| Number of trafficked person assisted/services provided | 925 | 250 |  | 0 |  |  | yes
| Number of LGU Social Workers trained to provide psychosocial recovery, and social and economic reintegration services to victims-survivors of trafficking | 500 |  |  | #DIV/0! | not targeted for the third quarter |  | yes
| Number of regions with functional Recovery and Reintegration Network | 17 | 4 |  | 0 |  |  | yes
| Centers upgraded to accommodate victims-survivors of trafficking | 6 |  |  |  | not targeted for the third quarter
MFO 4
Services for Center-Based and Community-Based Clients
Centers and Institutions
| No. of beneficiaries served at the facilities | 13182 | 3295 |  | 0 |  |  | yes
| No. of client days of service at the facilities | 1642170 | 1642170 |  | 0 |  | This is an annual target thus, it can cut across the targets per quarter
| No. of clients released/discharged from the facilities | 7163 | 1791 |  | 0 |  |  | yes
| No. of client rehabilitated at the facilities | 6201 | 1551 |  | 0 |  |  | yes
Community-based Services | No. of community-based beneficiaries provided with protective services Individuals | 58892 | 13973 |  | 0 |  | rectify: annual target of 58,892. It should be 55,892. typographical error | yes
| No. of clients served at Crisis Intervention Unit (CIU) | 93803 | 23451 |  | 0 | Provision of services to disaster victims of tropical storm "Quinta" and other clients (using the Priority Development Assistance Fund (PDAF) in Region VI thru DSWD CIU contributes largely to the over performance of this indicator. |  | yes
Social Pension for Indigent Senior Citizens for ages 77 and above
| No. of indigent senior citizens provided with social pension for ages 77 and above | 240868 | 240868 |  | 0 | Reported accomplishment is only as of 31 March 2013. Completion of pay-out to all beneficiaries is targeted to be done within the month of April 2013 or the next month following the reference quarter. | adjustment of targets from 232,868 to 240,868 due to the additional 8,000 targets
Program for Street Children, Street families and IPs, especially Bajaus
| No. of street children and their families served at day/night centers/activity centers a. Street Children b. Street Families | Continuous provision of support services like skills training, livelihood, relocation to street children, street families, Ips and Bajaus | ANA |  |  |  | revised targets are based on the submission of STB last May 9 as per their validation made
| No. of street children provided with educational assistance | 2000 |  |  |  | Not targeted for the third quarter |  | yes
| No. Bajau families/street families provided with Balik Probinsya Assistance | 20 | 10 |  |  |  |  | yes
| No. of parents provided with livelihood assistance | 180 | 100 |  |  |  |  | yes
| No. of street families/Bajau families provided with permanent shelter | 80 |  |  |  | Not targeted for the first quarter |  | yes
| No. of bajau families provided with livelihood and capacity building activities | 500 | 150 |  |  |  |  | yes
Pantawid Pamilyang Pilipino Program (Conditional Cash Transfer)
No. of household beneficiaries
| No. of targeted: | 3809769 | 3809769 |  | 0 |  | targeted for CY 2013 but there are still adjustments as of April 2013
| Regions | 17 | 17
| Provinces | 79 | 79
| Cities/Municipalities | 143cities, 1,484mun. | 143cities, 1,484mun.
Foreign-Assisted Project KCI KC Additional Financing (AF) KC Millennium Challenge Corporation (MCC) | No. of areas covered by KALAHI-CIDSS
| Regions | 12 |  |  |  |  | adjusted the targets of KC based on their validation made last April 2013.
| Provinces | 36
| Municipalities | 158
| Barangays | 3789
| No. of household beneficiaries from completed community sub-projects | 396900 | 50064 |  | 0 |  | delete ko nalang kaya ung first quarter target
| No. of community development projects completed | 1764
No. of LGUs fully implemented/intitutionalized the KC process (LGUs that adopting features of the KC approach)
| Municipalities | 148
| Barangays | 3529
0
Prepared By: |  | Approved By:
___________________________ |  | _____________________________________
FLORITA R. VILLAR |  | CORAZON JULIANO-SOLIMAN
Undersecretay for Policy and Plans Group |  | Secretary
Highlighted in green are those indicators that were included in the 2013 APM but not reflected in the CY 2013 BEDs

## OcttoDec (hidden)
Department of Social Welfare and Development
Physical Report of Operation
(October to December 2013)
DEPARTMENT/AGENCY: Department of Social Welfare and Development
Key Program/activities/Projects (P/A/Ps) | Performance Indicators | Physical Targets |  | Actual | Percentage (%) of Accomplishment | Reason for Under/Over Performance (Variance)
|  | FY 2013 (Annual) | Oct to Dec | Oct to Dec
MFO 1
Services Relating to the Formulation of Policies, Plans and Programs | [7 empty] | Formula?
Policies and Plans Development | No. of policy/position papers prepared including policies on regional cooperation international treaties and conventions | 44 | 12 |  | 0 |  |  | yes
| No. of policy notes issued | 4 | 1 |  | 0 |  |  | yes
| No. of policy guidelines developed/enhanced | 9 | 2 |  | 0 |  |  | yes
| No. of LGUs monitored complying to national and local laws/polices | 573 | 143 |  | 0 |  |  | yes
| No. of LGUs with SWD sectoral plans (cities,municipalities) | 678 | 170 |  | 0 |  |  | yes
| No. of sectoral plans and implementation report prepared | 6 | 6 |  | 0
| No. of research developed /implemented / completed | 8 | 2 |  | 0 |  |  | yes
| E-Services Upgraded | For enhancement | For enhancement
| SWD Geographic Information System (GIS) Developed | Continuous Updating | Continuous Updating
Social Welfare Development Reform Project (SWDRP) | National Convergence Framework on SP | Adoption of National Convergence Framework |  |  |  | Not targeted for the fourth quarter |  | yes
| Five (5) year Social Protection Plan | Implementation of 5 year SP Plan |  |  |  | Not targeted for the fourth quarter |  | yes
| Social Protection Handbook (draft) | 1 |  |  |  | Not targeted for the fourth quarter |  | yes
| Policies/Research Studies on Social Protection | 2 | 2 |  |  | deleted by PRD?
| Manual on Risk and Vulnerability (SP VAM) | 1 |  |  |  | Not targeted for the fourth quarter |  | yes
| Monitoring and Evaluation Unit (establishment) | Maintained 1 Monitoring and Evaluation Unit | Maintained 1 Monitoring and Evaluation Unit
| Impact Evaluation Conducted | 2 | 1
| Operational Manual on M & E | 1 | 1 |  |  |  | Ask nalang Aljo
| Index and Measure on Prevalance rate of Risk and Vulnerabilies Assessment | 1
| Regional Sectoral participation Index Developed | 1
Program Development | No. of social technology developed/programs and services enhanced | 2 |  |  |  | Not targeted for the first quarter, all of the 5 targets are to be accomplished on the last quarter of CY 2013. | checked the submission of STB regarding the revision of STB's quarterly targets for CY 2013 | yes
| No. of social technology guidelines developed | 3 |  |  |  | Sttill not targeted for the second quarter however, there's a carry-over from last year's activity which was already reported on the fist quarter physical report of operations
| No. of manual developed and/or finalized | 2 |  |  |  | Not targeted for the second quarter. | STB has revised its targets for this year from 2 to 5 manuals/developed or finalized | yes
| No. of concept paper/program design and documentation completed | 4 |  |  |  | Sttill not targeted for the second quarter however, there's a carry-over from last year's activity which was already reported on the fist quarter physical report of operations | STB has submitted revised targets for CY 2013. Check the submission of STB.
| No. of foreign post established to deliver SWD services to Filipino nationals | 8 | 8
National Household Targeting System for Poverty Reduction (NHTS-PR)
| Targetting System for SWD programs | Maintained 1 Targeting System | Maintained 1 Targeting System
| No. of household assessed and included in the database | Maintained 10,909,456 HHs in the database | Maintained 10,909,456 HHs in the database
| Number of households identified as poor through the Proxy Means Test (PMT) | Maintained 5.2 Million households in the database | Maintained 5.2 Million households in the database
MFO 2
Standards Setting, Licensing and Accreditation Services
Standards Setting and Accreditation Services | No. of auxiliary SWDAs registered | 211 | 54 |  | 0 |  | check the submission of SB (or kay ate tess since nasa kanya ang consolidatio ng MFO 2 reports | yes
| No. of SWAs registered and licensed (NGOs licensed) | 191 | 48 |  | 0 |  |  | yes
| No. of SWAs accredited (NGOs accredited) | 96 | 23 |  | 0 |  |  | yes
| No. of SWD Service providers accredited ( marriage counsellors, social workers, handling court cases, day care workers) | 2987 | 726 |  | 0 |  |  | yes
| No. of service facilities accredited (Day Care Center;Senior Citizens Centers) | 2886 | 651 |  | 0 |  |  | yes
| No. of NGOs endorsed to the Department of Finance | As Need Arises (ANA) | ANA
| No. of Authorities issued to conduct National Fund Raising Campaigns | ANA | ANA
| No. of ABSNET clusters organized and strengthened | 61 | 61 |  | 0 |  | whole year target which was already accomplished last first quarter
Reform Agenda | Online database for SWADA/service providers completed | Maintained & Sustained Online Database | Maintained & Sustained Database
| Consultation meetings with ABSNET by Field Offices | 61 |  |  |  | annual targets
| Consultation meeting with National ABSNET Federation | 1 |  |  |  | annual targets |  | yes
| National Consultation Dialogues | 1 |  |  |  | annual targets |  | yes
| Development of Manual on Monitoring and Evaluation of SWADAs | 1 |  |  |  | annual targets | requested for deletion last 7 June 2012 | yes
| Evaluation of the Accreditation System for Social Welfare and Development Programs and Services | 5 |  |  |  | annual targets | requested to change the indicator to Development of a Quality Management System (QMS) Certifiable to ISO 9001:2008 for the DSWD Standards Bureau | yes
MFO 3
Provision of Support Services and Technical Assistance to Intermediaries
Support Services and Technical Assistance to Intermediaries | No. of existing SWD training modules developed | 13 | 6 |  |  |  |  | yes
| No. of existing SWD training modules enhanced | 40 | 10 |  | 0 |  |  | yes
| No. of training modules utilized by intermediaries | 73 | 19 |  | 0 |  |  | yes
| No. of trainings conducted | 278 | 70 |  | 0 |  |  | yes
| No. of SWD implementers trained | 3040 | 760 |  | 0 |  |  | yes
| No. of participants who completed training | 9683 | 2421 |  | 0 |  |  | yes
Social Welfare Development Reform Project (SWDRP) | Knowledge Management and Learning Division Established | Maintained 1 Knowledge Management and Learning Development | Maintained 1 Knowledge Management and Learning Development
| Knowledge Exchange Center Established | Maintained 1 Knowledge Exchange Center | Maintained 1 Knowledge Exchange Center
Disaster Relief Operations | No. of beneficiaries provided with relief assistance
| Families | ANA | ANA |  |  |  |  | yes
| Individuals | ANA | ANA |  |  |  |  | yes
No. of disaster affected LGUs provided augmentation support
| Provinces | ANA | ANA |  |  |  |  | yes
| Cities | ANA | ANA |  |  |  |  | yes
| Municipalities | ANA | ANA |  |  |  |  | yes
SEA Kaunlaran Program
No. of families provided with capital seed fund
| Pantawid Pamilya | 486586 | 174086 |  | 0 | Reflected figures are only those provided with capital seed fund by DSWD. However, through partneship with Micro-Finance Institutions, a total of 24,554 Pantawid Pamilya beneficiaries were provided with capital assistance. Further, skills-enhancement training on farming and production were given to 13,447 Pantawid Pamilya beneficiaries as a form of non-financial assistance and facilitated employment of 77 pantawid beneficiaries. | apply nalang siguro dito ung changes na gusto ni Dir. Geo-Ann
Non-Pantawid
Supplementary Feeding Program
| No. of Day Care Children provided with supplementary feeding | 1778274 | 1755034 |  | 0 | Accomplishments are as of the March 2013 of the Second Cycle of the program SY 2012-2013 | not clear ang targets for the second quarter based on the BED. Should it be the same based on their approved WFP?
Cash/Food for Work/Training Program for Internally Displaced Person (IDPs)
| No. of IDPs affected by typhoon and other calamities manmade/natural provided with cash/training/work | 253881.0153 | 253881.0153
Core Shelter
| No. of shelter units funded | ANA | ANA
| No. of shelter units completed/ongoing | ANA | ANA
| No. of families benefited | ANA | ANA
Payapa at Masaganang Pamayanan (PAMANA)
| No. of barangays for community-driven development projects in ARMM | 2159 | 540 |  | 0 |  |  | yes
Recovery and Reintegration Program for Victims-Survivors of Trafficking
| Number of trafficked person assisted/services provided | 925 | 175 |  | 0 |  |  | yes
| Number of LGU Social Workers trained to provide psychosocial recovery, and social and economic reintegration services to victims-survivors of trafficking | 500 |  |  | #DIV/0! | not targeted for the fourth quarter |  | yes
| Number of regions with functional Recovery and Reintegration Network | 17 | 4 |  | 0 |  |  | yes
| Centers upgraded to accommodate victims-survivors of trafficking | 6 | 6 |  |  | not targeted for the fourth quarter
MFO 4
Services for Center-Based and Community-Based Clients
Centers and Institutions
| No. of beneficiaries served at the facilities | 13182 | 3295 |  | 0 |  |  | yes
| No. of client days of service at the facilities | 1642170 | 1642170 |  | 0 |  | This is an annual target thus, it can cut across the targets per quarter
| No. of clients released/discharged from the facilities | 7163 | 1790 |  | 0 |  |  | yes
| No. of client rehabilitated at the facilities | 6201 | 1550 |  | 0 |  |  | yes
Community-based Services | No. of community-based beneficiaries provided with protective services Individuals | 58892 | 13973 |  | 0 |  | rectify: annual target of 58,892. It should be 55,892. typographical error | yes
| No. of clients served at Crisis Intervention Unit (CIU) | 93803 | 23450 |  | 0 | Provision of services to disaster victims of tropical storm "Quinta" and other clients (using the Priority Development Assistance Fund (PDAF) in Region VI thru DSWD CIU contributes largely to the over performance of this indicator. |  | yes
Social Pension for Indigent Senior Citizens for ages 77 and above
| No. of indigent senior citizens provided with social pension for ages 77 and above | 240868 | 240868 |  | 0 | Reported accomplishment is only as of 31 March 2013. Completion of pay-out to all beneficiaries is targeted to be done within the month of April 2013 or the next month following the reference quarter. | adjustment of targets from 232,868 to 240,868 due to the additional 8,000 targets
Program for Street Children, Street families and IPs, especially Bajaus
| No. of street children and their families served at day/night centers/activity centers a. Street Children b. Street Families | Continuous provision of support services like skills training, livelihood, relocation to street children, street families, Ips and Bajaus | ANA |  |  |  | revised targets are based on the submission of STB last May 9 as per their validation made
| No. of street children provided with educational assistance | 2000 |  |  |  | Not targeted for the fourth quarter |  | yes
| No. Bajau families/street families provided with Balik Probinsya Assistance | 20 | 10 |  |  |  |  | yes
| No. of parents provided with livelihood assistance | 180 |  |  |  | Not targeted for the first quarter |  | yes
| No. of street families/Bajau families provided with permanent shelter | 80 | 80 |  |  |  |  | yes
| No. of bajau families provided with livelihood and capacity building activities | 500 | 200 |  |  |  |  | yes
Pantawid Pamilyang Pilipino Program (Conditional Cash Transfer)
No. of household beneficiaries
| No. of targeted: | 3809769 | 3809769 |  | 0 |  | targeted for CY 2013 but there are still adjustments as of April 2013
| Regions | 17 | 17
| Provinces | 79 | 79
| Cities/Municipalities | 143cities, 1,484mun. | 143cities, 1,484mun.
Foreign-Assisted Project KCI KC Additional Financing (AF) KC Millennium Challenge Corporation (MCC) | No. of areas covered by KALAHI-CIDSS
| Regions | 12 |  |  |  |  | adjusted the targets of KC based on their validation made last April 2013.
| Provinces | 36
| Municipalities | 158
| Barangays | 3789
| No. of household beneficiaries from completed community sub-projects | 396900 | 50064 |  | 0 |  | delete ko nalang kaya ung first quarter target
| No. of community development projects completed | 1764
No. of LGUs fully implemented/intitutionalized the KC process (LGUs that adopting features of the KC approach)
| Municipalities | 148
| Barangays | 3529
0
Prepared By: |  | Approved By:
___________________________ |  | _____________________________________
FLORITA R. VILLAR |  | CORAZON JULIANO-SOLIMAN
Undersecretay for Policy and Plans Group |  | Secretary
Highlighted in green are those indicators that were included in the 2013 APM but not reflected in the CY 2013 BEDs

## Jan to June
Department of Social Welfare and Development
Physical Report of Operation
(January to June 2014)
DEPARTMENT/AGENCY: Department of Social Welfare and Development
Program/activities/Projects MFO | Performance Indicators | Physical Targets |  | Actual | Percentage (%) of Accomplishment | Reason for Under/Over Performance (Variance)
|  | FY 2014 (Annual) | Jan to June | Jan to June
MFO 1: Social Protection Policy Services | QUANTITY No. of policies updated, issued and disseminated
| No. of policy notes issued | 4 | 2 | 1 | 50%
| No. of policy guidelines developed/ enhanced | 10 | 5 | 2 | 40%
| No. of sectoral plans and implementation report prepared | 6 | 6 | 6 | 100%
| QUALITY Average % of Members of Congress, intermediaries and other stakeholders that rate policies as good or better | 90% |  |  |  | Survey is not scheduled in the second quarter
| TIMELINESS % of policies that are updated, issued and disseminated in the last three (3) years | 75% | 75% | 100%
MFO 2: Social Protection Services | QUANTITY No. of persons assisted
No. of persons provided with residential care
Centers and Institutions
| No. of beneficiaries served at the facilities | 13340 | 6670 | 10820 | 162.2%
No. of individuals assisted (non-residential)
Community-based
| No. of community-based beneficiaries provided with protective services | 157179 | 75426 | 63157 | 83.73%
| Individuals | 58686 | 31104 | 23097 | 74.26%
| Clients served at Crisis Intervention Unit (CIU) | 98493 | 44322 | 40060 | 90.38%
Disaster Relief Operations
No. of beneficiaries provided with relief assistance
| Families | 1150231 |  | 324764 | 28.23% | January to July accomplishment
| Individuals | 5331058 |  | 1569488 | 29.44% | January to July Accomplishment
| QUALITY % of assisted persons for the last three (3) years who were found ineligible (no more than averaged 5%) | 5% | 5% | 0% |  |  | based on FO reports
| TIMELINESS 1 % of applications for non-residential assistance that are processed within 24 hours. | 90% | 90% | 100% |  |  | based on FO reports
| TIMELINESS 2 % of applications for residential assistance that are processed within 24 hours. | 100% | 100% | 100% |  |  | based on FO reports
Supplementary Feeding Program
| No. of Day Care/School Children provided with supplementary feeding | 2568811 |  | 1692843 |  | Accomplishment is cumulative as of June 2014 of the third cycle implementation (SY 2013-2014), with target of 1,778,274
Social Pension for Indigent Senior Citizens for ages 77 and above
| No. of indigent senior citizens with social pension for ages 77 and above | 479080 | 479080 | 19591 | 4.089% | Due to the special provision stipulated under the General Appropriation Act (GAA) for CY 2014 that states “Social Pension grants will be provided only to those social pensioners who are registered in the Listahanan database“ . Hence, the NHTO conducted special validation to the existing non-NHTS social pensioners for inclusion in the database.
Recovery and Reintegration Program for Trafficked Persons
| No. of trafficked person assisted | 1000 | 450 | 1075 | 238.9% | Included in the accomplishment are those rescued, offloaded by competent authorities such as Immigration Officers, port authorities and intercepted potential TIP victims in the transit areas like NCR, Region III and IX Further, the anti-trafficking task force in Tawi-Tawi has actively conducted rescue operation and interception of potential TIP clients.
Comprehensive Program for Street Children, Street Families and IPs, especially Bajaus
| No. of street children served | 3000 | 1000 | 2202 | 220.2% | Accomplishment was based on the adjusted targets set due to the World Economic Forum held last May 2014 in NCR.
| No. of Sama-Bajau children served | 606 |  | 200
No. of households assisted (non-residential)
Pantawid Pamilyang Pilipino Program (Conditional Cash Transfer)
| No. of household beneficiaries | 4329769 | 4329769 | 4088342 | 94.42%
Modified Conditional Cash Transfer e/
| No. of household beneficiaries | 131963 | 131963 | 2325 | 1.762%
| No. of children beneficiaries - CCT extended Coverage until High School | 10196437 | 10196437 | 7399463.3333
No. of families assisted (non-residential)
Sustainable Livelihood Program
No. of families to be served through ME Development
| Pantawid Pamilya | 77912 | 42852 | 55913 | 130.5%
| No. of household facilitated for employment | 33402 | 18371 | 2503 | 13.62%
Comprehensive Program for Street Children, Street Families and IPs, especially Bajaus
| No. of street families served | 600 | 300 | 329 | 109.7% | Accomplishment was based on the adjusted targets set due to the World Economic Forum held last May 2014 in NCR.
| No. of Bajau families served | 700 |  | 161 | [5 empty] | 0
No. of communities assisted (non-residential)
Kapit-bisig Laban sa Kahirapan - Comprehensive and Integrated Delivery of Social Services (Kalahi-CIDSS)
No. of areas covered
| Region | 14 |  | 6 | 42.86%
| Province | 57 |  | 20 | 35.09%
| Municipality | 734 |  | 113 | 15.4%
| Barangay | 17675 |  | 2743 | 15.52%
| No. of community development projects funded/completed |  | 490 | 461 | 94.08%
Implementation of various programs/projects for LGUs (Priority Programs)
Grassroots Participatory Budgeting
No. of LGUs benefitted from the following programs:
| Protective Services |  |  |  |  | Validation of projects and completion of required documents are still ongoing
SEA-K (No. of Municipalities served)
NCDDP
Implementation and Monitoring of PAMANA Program
No. of Provinces
No. of Barangays
| NCDDP | 1,380 Brgys; 18 Provinces |  | 251 | 19% |  |  |  | All targeted areas are in social preparation stage
| SLP | 470 Brgys; 9 Provinces |  | 133 completed | 28% |  |  |  | Field Offices are currently in the process of procuring the equipment/common service facilities for the projects
| PAMANA Pillar 2 | 268 Brgys; 5 Provinces |  |  |  | All targeted areas are in social preparation stage up to the delivery of building materials.
MFO 3: Capacity Building Services | PI SET 1
| QUANTITY No. of persons provided with training services | 9849 | 5826 | 13012 | 223.3% | Due to the Performance Review and Evaluation Workshop (PREW) of Social Pension, Supplementary Feeding Program training among others conducted by the Field Offices with the LGUs. | CBB - | FO - 3,579
| QUALITY % of trainees who rate training courses satisfactory or better | 90% | 90% | 65.85% |  |  | CBB - | FO - 94%
| TIMELINESS % of training courses that completed as designed | 95% | 95% | 95.13% |  |  | CBB - | FO - 98%
PI SET 2
| QUANTITY No. of LGUs and other intermediaries provided with technical assistance | 1599 | 716 | 1942 | 271.2% | Includes accomplishments of Field Offices | PSB - | FO - 868
| QUALITY % of intermediaries who rate assistance as good or better | 90% | 90% | 96% |  |  | PSB - | FO - 96%
| TIMELINESS % of technical services provided within X days of request | 100% | 100% | 100% |  |  | PSB - | FO - 99%
PI SET 3
| QUANTITY No. of LGUs and other intermediaries provided with resource augmentation | 712 | 471 | 1611 | 342% | Includes accomplishments of Field Offices | DRRROO - | FO - 451
| QUALITY % of recipients who rate assistance as good or better | 90% | 90% | 94% |  |  | DRRROO -
| TIMELINESS % of resource augmentation initiative requests acted upon within three (3) days. | 90% | 90% | 100% |  |  | DRRROO - | FO - 99%
MFO 4: Regulatory Services | PI SET 1 | [7 empty] | Target
| QUANTITY No. of social welfare and development agencies and service providers licensed or accredited | 3588 | 1627 | 1902 | 116.9% | Includes accomplishment of FOs: SB (SWDA licensed) - 24 SB (SP accredited) - 108 FO (SWA licensed) - 74 FO (SP accredited) - 1,696 | SB (SWDA licensed) - 24 SB (SWDA accredited) - 8 SB (SP accredited) - 108 | FO (SWA licensed) - 74 FO (SP accredited) - 1696 | SB (SWDA licensed) - 15 SB (SWDA accredited) - 8 SB (SP accredited) - 82 | FO (SWA licensed) - 72 FO (SP accredited) - 1104
| QUALITY % of licensed and accredited SWDAs/ service providers with a recorded violation within the last two (2) years | 100% complaints acted upon | 100% complaints acted upon | 100% complaints acted upon |  | Includes accomplishments of Field Offices | SB - 0 | FO - 100%
| TIMELINESS % of licenses issued in 15 days or less from receipt of compliant application | 100% | 100% | 80% |  | Includes accomplishments of Field Offices | SB - 80%
PI SET 2
| QUANTITY Number of violations/ complaints received | 10 | 8 | 6 | 75% | Includes accomplishments of Field Offices | SB - 0 | FO - 6
| QUALITY Number of persons and entities with 2 or more recorded violations/ complaints in the last three (3) years as a % of total number of violators in the last three (3) years. | 100% complaints acted upon | 100% complaints acted upon | 100% complaints acted upon |  | Includes accomplishments of Field Offices | SB - 0 | FO - 100%
| TIMELINESS Percentage of detected violations/complaints that are resolved within seven (7) working days | 100% complaints acted upon | 100% complaints acted upon | 100% complaints acted upon |  | Includes accomplishments of Field Offices | SB - 0 | FO - 0
Locally-Funded Projects | National Household Targeting System for Poverty Reduction
| Number of households identified as poor through the Proxy Means Test (PMT) | 5.2 million poor households | 5.2 million poor households | 5.2 million poor households
0
Prepared By: |  | Approved By:
___________________________ |  | _____________________________________
FLORITA R. VILLAR |  | CORAZON JULIANO-SOLIMAN
Undersecretay for Policy and Plans Group |  | Secretary
Note on D46: acer: used the original submitted targets of Pantawid. Not the one refelcted in the GAA for CY 2014

## Jan-Dec
Department of Social Welfare and Development
Physical Report of Operation
(January to December 2014)
DEPARTMENT/AGENCY: Department of Social Welfare and Development
Program/activities/Projects MFO | Performance Indicators | Physical Targets | Actual | Percentage (%) of Accomplishment | Reason for Under/Over Performance (Variance)
|  | FY 2014 (Annual) | Jan to Dec.
MFO 1: Social Protection Policy Services | QUANTITY No. of policies updated, issued and disseminated
| No. of policy notes issued | 4 | 4 | 100%
| No. of policy guidelines developed/ enhanced | 10 | 9 | 90%
| No. of sectoral plans and implementation report prepared | 6 | 6 | 100%
| QUALITY Average % of intermediaries and other stakeholders that rate policies as good or better | 90% | 87.21% | 96.9% | Out of the 86 respondents 72.09 % rated better and 15.12% rated good which totalled to 87.21% meanwhile the remaining 12.79 % rated best
| TIMELINESS % of policies that are updated, issued and disseminated in the last three (3) years | 75% | 100% | 133.3%
MFO 2: Social Protection Services | QUANTITY No. of persons assisted
No. of persons provided with residential care
Centers and Institutions
| No. of beneficiaries served at the facilities | 13340 | 16906 | 126.7%
No. of individuals assisted (non-residential)
Community-based
| No. of community-based beneficiaries provided with protective services | 157179 | 310231 | 197.4%
| Individuals | 58686 | 43889 | 74.79%
| Clients served at Crisis Intervention Unit (CIU) | 98493 | 266342 | 270.4%
Disaster Relief Operations
No. of beneficiaries provided with relief assistance
| Families | 1150231 | 890311 | 77.4% | Total number of families/persons provided with family food packs (FFP), food items and other forms of assistance ( e.g. trvel expense, medical assistance) | 619,654 +324,767
| Individuals | 5331058 | 4015997 | 75.33% |  | 1569488+2,794,547
| QUALITY % of assisted persons for the last three (3) years who were found ineligible (no more than averaged 5%) | 5% | 0% | 0% | There are no ineligible reported.All referred and walk-in clients are being assessed/evaluated and provided their immediate needs (within 24 hours) | based on FO reports
| TIMELINESS 1 % of applications for non-residential assistance that are processed within 24 hours. | 90% | 100% | 111.1% |  | based on FO reports
| TIMELINESS 2 % of applications for residential assistance that are processed within 24 hours. | 100% | 100% | 100% |  | based on FO reports
Supplementary Feeding Program
| No. of Day Care/School Children provided with supplementary feeding | 2568811 | 1819925 | 70.85% | Delayed submission of liquidation report of some day care workers/LGUs that affects the continuity of the supplementary feeding implementation.
Social Pension for Indigent Senior Citizens for ages 77 and above
| No. of indigent senior citizens with social pension for ages 77 and above | 479080 | 452836 | 94.52% |  | done
Recovery and Reintegration Program for Trafficked Persons
| No. of trafficked person assisted | 1000 | 1075 | 107.5%
Comprehensive Program for Street Children, Street Families and IPs, especially Bajaus
| No. of street children served | 3000 | 3712 | 123.7% |  | 4756 street children | less 1206 bajaus
| No. of Sama-Bajau children served | 606 | 2459 | 405.8% |  | 1785 street families | less1115
| No. of street families served | 600 | 608 | 101.3%
| No. of Bajau families served | 700 | 1371 | 195.9% |  |  |  |  | 0
No. of households assisted (non-residential)
| Pantawid Pamilyang Pilipino Program (Conditional Cash Transfer) | 4461732 | 4478562
| No. of household beneficiaries | 4329769 | 4260185 | 98.39%
Modified Conditional Cash Transfer e/
| No. of household beneficiaries | 131963 | 218377 | 165.5%
No. of families assisted (non-residential)
Sustainable Livelihood Program
| No. of families to be served through ME Development |  | 133517
| Pantawid Pamilya | 77912 | 123890 | 159%
| No. of household facilitated for employment | 33402 | 9627 | 28.82% | Limited employment opportunities in the areas served by the programs
Kapit-bisig Laban sa Kahirapan - Comprehensive and Integrated Delivery of Social Services (Kalahi-CIDSS)
No. of areas covered
| Region | 14 | 14 | 100%
| Province | 57 | 57 | 100%
| Municipality | 734 | 666 | 90.74%
| Barangay | 17351 | 16080 | 92.67%
| No. of community development projects funded/completed | 980 | 954 | 97.35%
Implementation of various programs/projects for LGUs (Priority Programs)
Grassroots Participatory Budgeting
No. of LGUs benefitted from the following programs:
| Protective Services | 627 | 951 | 151.7%
| SEA-K (No. of Municipalities served) | 938 mun | 35 completed | 4% | 77 projects are on-going 847 projects are pipelined 138 are undergoing projects proposed
| NCDDP | 339 mun. 72 prov | 339 mun and 72 prov | 100%
Implementation and Monitoring of PAMANA Program
No. of Provinces
No. of Barangays
| NCDDP | 1,380 Brgys; 18 Provinces | 1380 brgys and 18 provinces | 100% |  |  |  | All targeted areas are in social preparation stage
| SLP | 470 brgys; 9 provinces | 74 completed |  | 65 projects are already for funding, 331 are on-going project proposals |  |  | Field Offices are currently in the process of procuring the equipment/common service facilities for the projects
| PAMANA Pillar 2 | 268 Brgys; 5 Provinces | 59 completed |  | 114 barangays are in procurement materials and 95 are on-going constructions
MFO 3: Capacity Building Services | PI SET 1
| QUANTITY No. of persons provided with training services | 9849 | 24923 | 253.1% | High accomplishment was attributed to: a) In relation to Department SG 3 (Functionality of LSWDOs), there were additional LGUs provided with training/orientation b) Inclusion of Pantawid Pamilya Parent Leaders c) including trainings from foreign funded such as ECCD | CBB - | FO - 3,579 | fo
| QUALITY % of trainees who rate training courses satisfactory or better | 90% | 90% | 100% |  | CBB - | FO - 94%
| TIMELINESS % of training courses that completed as designed | 95% | 95.13% | 100.1% |  | CBB - | FO - 98%
PI SET 2
| QUANTITY No. of LGUs and other intermediaries provided with technical assistance | 1599 | 2325 | 145.4% | Includes accomplishments of Field Offices | PSB - | FO - 868
| QUALITY % of intermediaries who rate assistance as good or better | 90% | 96.75% | 107.5% |  | PSB - | FO - 96%
| TIMELINESS % of technical services provided within X days of request | 100% | 99.01% | 99.01% |  | PSB - | FO - 99%
PI SET 3
| QUANTITY No. of LGUs and other intermediaries provided with resource augmentation | 712 | 1703 | 239.2% | Includes accomplishments of Field Offices | DRRROO - | FO - 451
| QUALITY % of recipients who rate assistance as good or better | 90% | 94.94% | 105.5% |  | DRRROO -
| TIMELINESS % of resource augmentation initiative requests acted upon within three (3) days. | 90% | 99.59% | 110.7% |  | DRRROO - | FO - 99%
MFO 4: Regulatory Services | PI SET 1 | [6 empty] | Target
| QUANTITY No. of social welfare and development agencies and service providers licensed or accredited | 3588 | 4568 | 127.3% | Includes accomplishment of FOs: SB (SWDA licensed) -48 SB (SP accredited) - 63 swmc, mc118, swa accretd163 FO (SWA licensed) -148 FO (SP accredited) -4029 | SB (SWDA licensed) - 24 SB (SWDA accredited) - 8 SB (SP accredited) - 108 | FO (SWA licensed) - 74 FO (SP accredited) - 1696 | SB (SWDA licensed) - 15 SB (SWDA accredited) - 8 SB (SP accredited) - 82 | FO (SWA licensed) - 72 FO (SP accredited) - 1104
| QUALITY % of licensed and accredited SWDAs/ service providers with a recorded violation within the last two (2) years | 100% complaints acted upon | 100% complaints acted upon | 100% complaints acted upon | Includes accomplishments of Field Offices | SB - 0 | FO - 100%
| TIMELINESS % of licenses issued in 15 days or less from receipt of compliant application | 100% | 100% | 100% | Includes accomplishments of Field Offices | SB - 80%
PI SET 2
| QUANTITY Number of violations/ complaints received | 10 | 20 | 200% | Includes accomplishments of Field Offices | SB - 0 | FO - 6
| QUALITY Number of persons and entities with 2 or more recorded violations/ complaints in the last three (3) years as a % of total number of violators in the last three (3) years. | 100% complaints acted upon | 100% complaints acted upon | 100% complaints acted upon | Includes accomplishments of Field Offices | SB - 0 | FO - 100%
| TIMELINESS Percentage of detected violations/complaints that are resolved following due process per approved guidelines | 100% complaints acted upon | 100% complaints acted upon | 100% complaints acted upon | Includes accomplishments of Field Offices | SB - 0 | FO - 0
Locally-Funded Projects | National Household Targeting System for Poverty Reduction
| Number of households identified as poor through the Proxy Means Test (PMT) | 5.2 million poor households | 5.2 million poor households | 100%
Prepared By: |  | Approved By:
___________________________ |  | _____________________________________
FLORITA R. VILLAR |  | CORAZON JULIANO-SOLIMAN
Undersecretay for Policy and Plans Group |  | Secretary
GBG/CBL/TESS

## jan-sept
Department of Social Welfare and Development
Physical Report of Operation
(January to September 2014)
DEPARTMENT/AGENCY: Department of Social Welfare and Development
Program/activities/Projects MFO | Performance Indicators | Physical Targets |  | Actual | Percentage (%) of Accomplishment | Reason for Under/Over Performance (Variance)
|  | FY 2014 (Annual) | Jan to Sep | Jan to Sep
MFO 1: Social Protection Policy Services | QUANTITY No. of policies updated, issued and disseminated
| No. of policy notes issued | 4 | 3 | 2 | 66.67% | The other policy notes will be issued in the 4th qtr
| No. of policy guidelines developed/ enhanced | 10 | 8 | 5 | 62.5%
| No. of sectoral plans and implementation report prepared | 6 | 6 | 6 | 100%
| QUALITY Average % of intermediaries and other stakeholders that rate policies as good or better | 90% |  |  |  | Survey is not scheduled in the second quarter
| TIMELINESS % of policies that are updated, issued and disseminated in the last three (3) years | 75% | 75% | 100%
MFO 2: Social Protection Services | QUANTITY No. of persons assisted
No. of persons provided with residential care
Centers and Institutions
| No. of beneficiaries served at the facilities | 13340 | 10005 | 14695 | 146.9%
No. of individuals assisted (non-residential)
Community-based
| No. of community-based beneficiaries provided with protective services | 157179 | 117696 | 165123 | 140.3%
| Individuals | 58686 | 42841 | 29847 | 69.67%
| Clients served at Crisis Intervention Unit (CIU) | 98493 | 74855 | 135276 | 180.7%
Disaster Relief Operations
No. of beneficiaries provided with relief assistance
| Families | 1150231 |  | 944421 | 82.11% |  | 619,654 +324,767
| Individuals | 5331058 |  | 43640035 | 818.6% |  | 1569488+2,794,547
| QUALITY % of assisted persons for the last three (3) years who were found ineligible (no more than averaged 5%) | 5% | 5% | 0% |  |  | based on FO reports
| TIMELINESS 1 % of applications for non-residential assistance that are processed within 24 hours. | 90% | 90% | 100% |  |  | based on FO reports
| TIMELINESS 2 % of applications for residential assistance that are processed within 24 hours. | 100% | 100% | 100% |  |  | based on FO reports
Supplementary Feeding Program
| No. of Day Care/School Children provided with supplementary feeding | 2568811 |  | 1692843 |  | Accomplishment is cumulative as of Sept. 2014 of the 4th cycle implementation (SY 2013-2014), with target of 1,778,274
Social Pension for Indigent Senior Citizens for ages 77 and above
| No. of indigent senior citizens with social pension for ages 77 and above | 479080 | 479080 | 133592 | 27.89% | A total of 133,592 or 28% social pensioners were served as of Aug. 2014. It included the 19,591 paid beneficiaries as of June 30, 2014 and 114,001 beneficiaries with payroll for the month of July 2014 in all regions except ARMM. | done
Recovery and Reintegration Program for Trafficked Persons
| No. of trafficked person assisted | 1000 | 750 | 1075 | 143.3% | Included in the accomplishment are those rescued, offloaded by competent authorities such as Immigration Officers, port authorities and intercepted potential TIP victims in the transit areas like NCR, Region III and IX Further, the anti-trafficking task force in Tawi-Tawi has actively conducted rescue operation and interception of potential TIP clients.
Comprehensive Program for Street Children, Street Families and IPs, especially Bajaus
| No. of street children served | 3000 | 2000 | 3550 | 177.5% | Accomplishment was based on the adjusted targets set due to the World Economic Forum held last May 2014 in NCR. | 4756 street children | less 1206 bajaus
| No. of Sama-Bajau children served | 606 | 404 | 1206 | 298.5% |  | 1785 street families | less1115
| No. of street families served | 600 | 500 | 670 | 134%
| No. of Bajau families served | 700 | 350 | 1115 | 318.6% |  |  |  |  | 0
No. of households assisted (non-residential)
Pantawid Pamilyang Pilipino Program (Conditional Cash Transfer)
| No. of household beneficiaries | 4329769 | 4329769 | 4173528 | 96.39%
Modified Conditional Cash Transfer e/
| No. of household beneficiaries | 131963 | 131963 | 152680 | 115.7%
No. of families assisted (non-residential)
Sustainable Livelihood Program
No. of families to be served through ME Development
| Pantawid Pamilya | 77912 | 58434 | 73610 | 126%
| No. of household facilitated for employment | 33402 | 25051 | 3134 | 12.51% | Limited employment opportunities in the areas served by the programs
Kapit-bisig Laban sa Kahirapan - Comprehensive and Integrated Delivery of Social Services (Kalahi-CIDSS)
No. of areas covered
| Region | 14 | 14 | 14 | 100%
| Province | 57 | 57 | 57 | 100%
| Municipality | 734 | 734 | 478 | 65.12%
| Barangay | 2743 | 17675 | 11903 | 67.34%
| No. of community development projects funded/completed |  | 735 | 739 | 100.5%
Implementation of various programs/projects for LGUs (Priority Programs)
Grassroots Participatory Budgeting
No. of LGUs benefitted from the following programs:
| Protective Services | 627 |  | 455 | 72.56%
| SEA-K (No. of Municipalities served) | 938 mun |  | 25 mun. | 2.6% | 7 projects are on-going 662 projects are pipelined 394 are undergoing projects proposed writing 11 are still for validation
| NCDDP | 339 mun. 72 prov |  | 339 mun. 72 prov | 100%
Implementation and Monitoring of PAMANA Program
No. of Provinces
No. of Barangays
| NCDDP | 1,380 Brgys; 18 Provinces |  | 1,380 Brgys; 18 Provinces | 100% | 2013 , baclogs overlapping with implementation |  |  | All targeted areas are in social preparation stage
| SLP | 470 brgys; 9 provinces | 470 |  |  | 432 projects are already for funding, 38 are on-going project proposal writing which expected to finished by 31 October 2014 |  |  | Field Offices are currently in the process of procuring the equipment/common service facilities for the projects
| PAMANA Pillar 2 | 268 Brgys; 5 Provinces | 268 |  |  | 260 areas are in social preparation stage up to the delivery of building materials. 8 (eight) are on-going constructions
MFO 3: Capacity Building Services | PI SET 1
| QUANTITY No. of persons provided with training services | 9849 | 7796 | 19275 | 247.2% | Due to the Performance Review and Evaluation Workshop (PREW) of Social Pension, Supplementary Feeding Program training among others conducted by the Field Offices with the LGUs. | CBB - | FO - 3,579 | fo
| QUALITY % of trainees who rate training courses satisfactory or better | 90% | 90% | 90% |  |  | CBB - | FO - 94%
| TIMELINESS % of training courses that completed as designed | 95% | 95% | 95.13% |  |  | CBB - | FO - 98%
PI SET 2
| QUANTITY No. of LGUs and other intermediaries provided with technical assistance | 1599 | 1159 | 1842 | 158.9% | Includes accomplishments of Field Offices | PSB - | FO - 868
| QUALITY % of intermediaries who rate assistance as good or better | 90% | 90% | 99% |  |  | PSB - | FO - 96%
| TIMELINESS % of technical services provided within X days of request | 100% | 100% | 100% |  |  | PSB - | FO - 99%
PI SET 3
| QUANTITY No. of LGUs and other intermediaries provided with resource augmentation | 712 | 582 | 1588 | 272.9% | Includes accomplishments of Field Offices | DRRROO - | FO - 451
| QUALITY % of recipients who rate assistance as good or better | 90% | 90% | 94% |  |  | DRRROO -
| TIMELINESS % of resource augmentation initiative requests acted upon within three (3) days. | 90% | 90% | 100% |  |  | DRRROO - | FO - 99%
MFO 4: Regulatory Services | PI SET 1 | [7 empty] | Target
| QUANTITY No. of social welfare and development agencies and service providers licensed or accredited | 3588 | 2638 | 2946 | 111.7% | Includes accomplishment of FOs: SB (SWDA licensed) - 35 SB (SP accredited) - 153 FO (SWA licensed) - 113 FO (SP accredited) -2645 DCC | SB (SWDA licensed) - 24 SB (SWDA accredited) - 8 SB (SP accredited) - 108 | FO (SWA licensed) - 74 FO (SP accredited) - 1696 | SB (SWDA licensed) - 15 SB (SWDA accredited) - 8 SB (SP accredited) - 82 | FO (SWA licensed) - 72 FO (SP accredited) - 1104
| QUALITY % of licensed and accredited SWDAs/ service providers with a recorded violation within the last two (2) years | 100% complaints acted upon | 100% complaints acted upon | 100% complaints acted upon |  | Includes accomplishments of Field Offices | SB - 0 | FO - 100%
| TIMELINESS % of licenses issued in 15 days or less from receipt of compliant application | 100% | 100% | 100% |  | Includes accomplishments of Field Offices | SB - 80%
PI SET 2
| QUANTITY Number of violations/ complaints received | 10 | 9 | 18 | 200% | Includes accomplishments of Field Offices | SB - 0 | FO - 6
| QUALITY Number of persons and entities with 2 or more recorded violations/ complaints in the last three (3) years as a % of total number of violators in the last three (3) years. | 100% complaints acted upon | 100% complaints acted upon | 100% complaints acted upon |  | Includes accomplishments of Field Offices | SB - 0 | FO - 100%
| TIMELINESS Percentage of detected violations/complaints that are resolved following due process per approved guidelines | 100% complaints acted upon | 100% complaints acted upon | 100% complaints acted upon |  | Includes accomplishments of Field Offices | SB - 0 | FO - 0
Locally-Funded Projects | National Household Targeting System for Poverty Reduction
| Number of households identified as poor through the Proxy Means Test (PMT) | 5.2 million poor households | 5.2 million poor households | 5.2 million poor households | 100%
0
Prepared By: |  | Approved By:
___________________________ |  | _____________________________________
FLORITA R. VILLAR |  | CORAZON JULIANO-SOLIMAN
Undersecretay for Policy and Plans Group |  | Secretary
GBG/CBL/TESS

## Jan to June (2)
Department of Social Welfare and Development
Physical Report of Operation
(January to June 2014)
DEPARTMENT/AGENCY: Department of Social Welfare and Development
Program/activities/Projects MFO | Performance Indicators | Physical Targets |  | Actual | Percentage (%) of Accomplishment | Reason for Under/Over Performance (Variance)
|  | FY 2014 (Annual) | Jan to June | Jan to June
MFO 1: Social Protection Policy Services | QUANTITY No. of policies updated, issued and disseminated
| No. of policy notes issued | 4 | 2 | 1 | 50% | The other policy notes will be issued in the 3rd qtr
| No. of policy guidelines developed/ enhanced | 10 | 5 | 2 | 40% | Most policies issued in the 1st sem are internal policies
| No. of sectoral plans and implementation report prepared | 6 | 6 | 6 | 100%
| QUALITY Average % of Members of Congress, intermediaries and other stakeholders that rate policies as good or better | 90% |  |  |  | Survey is not scheduled in the second quarter
| TIMELINESS % of policies that are updated, issued and disseminated in the last three (3) years | 75% | 75% | 100%
MFO 2: Social Protection Services | QUANTITY No. of persons assisted
No. of persons provided with residential care
Centers and Institutions
| No. of beneficiaries served at the facilities | 13340 | 6670 | 10820 | 162.2%
No. of individuals assisted (non-residential)
Community-based
| No. of community-based beneficiaries provided with protective services | 157179 | 75426 | 63157 | 83.73%
| Individuals | 58686 | 31104 | 23097 | 74.26%
| Clients served at Crisis Intervention Unit (CIU) | 98493 | 44322 | 40060 | 90.38%
Disaster Relief Operations
No. of beneficiaries provided with relief assistance
| Families | 1150231 |  | 324764 | 28.23% | January to July accomplishment | Aug to sept 619,654
| Individuals | 5331058 |  | 1569488 | 29.44% | January to July Accomplishment | individuals 2,794,547
| QUALITY % of assisted persons for the last three (3) years who were found ineligible (no more than averaged 5%) | 5% | 5% | 0% |  |  | based on FO reports
| TIMELINESS 1 % of applications for non-residential assistance that are processed within 24 hours. | 90% | 90% | 100% |  |  | based on FO reports
| TIMELINESS 2 % of applications for residential assistance that are processed within 24 hours. | 100% | 100% | 100% |  |  | based on FO reports
Supplementary Feeding Program
| No. of Day Care/School Children provided with supplementary feeding | 2568811 |  | 1692843 |  | Accomplishment is cumulative as of June 2014 of the third cycle implementation (SY 2013-2014), with target of 1,778,274
Social Pension for Indigent Senior Citizens for ages 77 and above
| No. of indigent senior citizens with social pension for ages 77 and above | 479080 | 479080 | 19591 | 4.089% | Due to the special provision stipulated under the General Appropriation Act (GAA) for CY 2014 that states “Social Pension grants will be provided only to those social pensioners who are registered in the Listahanan database“ . Hence, the NHTO conducted special validation to the existing non-NHTS social pensioners for inclusion in the database.
Recovery and Reintegration Program for Trafficked Persons
| No. of trafficked person assisted | 1000 | 450 | 1075 | 238.9% | Included in the accomplishment are those rescued, offloaded by competent authorities such as Immigration Officers, port authorities and intercepted potential TIP victims in the transit areas like NCR, Region III and IX Further, the anti-trafficking task force in Tawi-Tawi has actively conducted rescue operation and interception of potential TIP clients.
Comprehensive Program for Street Children, Street Families and IPs, especially Bajaus
| No. of street children served | 3000 | 1000 | 2202 | 220.2% | Accomplishment was based on the adjusted targets set due to the World Economic Forum held last May 2014 in NCR.
| No. of Sama-Bajau children served | 606 |  | 200
No. of households assisted (non-residential)
Pantawid Pamilyang Pilipino Program (Conditional Cash Transfer)
| No. of household beneficiaries | 4329769 | 4329769 | 4088342 | 94.42%
Modified Conditional Cash Transfer e/
| No. of household beneficiaries | 131963 | 131963 | 2325 | 1.762%
| No. of children beneficiaries - CCT extended Coverage until High School | 10196437 | 10196437 | 7399463.3333
No. of families assisted (non-residential)
Sustainable Livelihood Program
No. of families to be served through ME Development
| Pantawid Pamilya | 77912 | 42852 | 55913 | 130.5%
| No. of household facilitated for employment | 33402 | 18371 | 2503 | 13.62%
Comprehensive Program for Street Children, Street Families and IPs, especially Bajaus
| No. of street families served | 600 | 300 | 329 | 109.7% | Accomplishment was based on the adjusted targets set due to the World Economic Forum held last May 2014 in NCR.
| No. of Bajau families served | 700 |  | 161 | [5 empty] | 0
No. of communities assisted (non-residential)
Kapit-bisig Laban sa Kahirapan - Comprehensive and Integrated Delivery of Social Services (Kalahi-CIDSS)
No. of areas covered
| Region | 14 |  | 6 | 42.86%
| Province | 57 |  | 20 | 35.09%
| Municipality | 734 |  | 113 | 15.4%
| Barangay | 17675 |  | 2743 | 15.52%
| No. of community development projects funded/completed |  | 490 | 461 | 94.08%
Implementation of various programs/projects for LGUs (Priority Programs)
Grassroots Participatory Budgeting
No. of LGUs benefitted from the following programs:
| Protective Services |  |  |  |  | Validation of projects and completion of required documents are still ongoing
SEA-K (No. of Municipalities served)
NCDDP
Implementation and Monitoring of PAMANA Program
No. of Provinces
No. of Barangays
| NCDDP | 1,380 Brgys; 18 Provinces |  | 251 | 19% |  |  |  | All targeted areas are in social preparation stage
| SLP | 470 Brgys; 9 Provinces |  | 133 completed | 28% |  |  |  | Field Offices are currently in the process of procuring the equipment/common service facilities for the projects
| PAMANA Pillar 2 | 268 Brgys; 5 Provinces |  |  |  | All targeted areas are in social preparation stage up to the delivery of building materials.
MFO 3: Capacity Building Services | PI SET 1
| QUANTITY No. of persons provided with training services | 9849 | 5826 | 13012 | 223.3% | Due to the Performance Review and Evaluation Workshop (PREW) of Social Pension, Supplementary Feeding Program training among others conducted by the Field Offices with the LGUs. | CBB - | FO - 3,579
| QUALITY % of trainees who rate training courses satisfactory or better | 90% | 90% | 65.85% |  |  | CBB - | FO - 94%
| TIMELINESS % of training courses that completed as designed | 95% | 95% | 95.13% |  |  | CBB - | FO - 98%
PI SET 2
| QUANTITY No. of LGUs and other intermediaries provided with technical assistance | 1599 | 716 | 1942 | 271.2% | Includes accomplishments of Field Offices | PSB - | FO - 868
| QUALITY % of intermediaries who rate assistance as good or better | 90% | 90% | 96% |  |  | PSB - | FO - 96%
| TIMELINESS % of technical services provided within X days of request | 100% | 100% | 100% |  |  | PSB - | FO - 99%
PI SET 3
| QUANTITY No. of LGUs and other intermediaries provided with resource augmentation | 712 | 471 | 1611 | 342% | Includes accomplishments of Field Offices | DRRROO - | FO - 451
| QUALITY % of recipients who rate assistance as good or better | 90% | 90% | 94% |  |  | DRRROO -
| TIMELINESS % of resource augmentation initiative requests acted upon within three (3) days. | 90% | 90% | 100% |  |  | DRRROO - | FO - 99%
MFO 4: Regulatory Services | PI SET 1 | [7 empty] | Target
| QUANTITY No. of social welfare and development agencies and service providers licensed or accredited | 3588 | 1627 | 1902 | 116.9% | Includes accomplishment of FOs: SB (SWDA licensed) - 24 SB (SP accredited) - 108 FO (SWA licensed) - 74 FO (SP accredited) - 1,696 | SB (SWDA licensed) - 24 SB (SWDA accredited) - 8 SB (SP accredited) - 108 | FO (SWA licensed) - 74 FO (SP accredited) - 1696 | SB (SWDA licensed) - 15 SB (SWDA accredited) - 8 SB (SP accredited) - 82 | FO (SWA licensed) - 72 FO (SP accredited) - 1104
| QUALITY % of licensed and accredited SWDAs/ service providers with a recorded violation within the last two (2) years | 100% complaints acted upon | 100% complaints acted upon | 100% complaints acted upon |  | Includes accomplishments of Field Offices | SB - 0 | FO - 100%
| TIMELINESS % of licenses issued in 15 days or less from receipt of compliant application | 100% | 100% | 80% |  | Includes accomplishments of Field Offices | SB - 80%
PI SET 2
| QUANTITY Number of violations/ complaints received | 10 | 8 | 6 | 75% | Includes accomplishments of Field Offices | SB - 0 | FO - 6
| QUALITY Number of persons and entities with 2 or more recorded violations/ complaints in the last three (3) years as a % of total number of violators in the last three (3) years. | 100% complaints acted upon | 100% complaints acted upon | 100% complaints acted upon |  | Includes accomplishments of Field Offices | SB - 0 | FO - 100%
| TIMELINESS Percentage of detected violations/complaints that are resolved within seven (7) working days | 100% complaints acted upon | 100% complaints acted upon | 100% complaints acted upon |  | Includes accomplishments of Field Offices | SB - 0 | FO - 0
Locally-Funded Projects | National Household Targeting System for Poverty Reduction
| Number of households identified as poor through the Proxy Means Test (PMT) | 5.2 million poor households | 5.2 million poor households | 5.2 million poor households
0
Prepared By: |  | Approved By:
___________________________ |  | _____________________________________
FLORITA R. VILLAR |  | CORAZON JULIANO-SOLIMAN
Undersecretay for Policy and Plans Group |  | Secretary
Note on D46: acer: used the original submitted targets of Pantawid. Not the one refelcted in the GAA for CY 2014